## Worksheet
Request for proposal RFP and Scope Of work for Clubhouse to Offices Renovation.
Total Covered area to be renovated: 554 sqm.
1. Scope of Work
The scope comprises the renovation of clubhouse to be offices and facilities including full renovation of WC, flooring replacement, painting works, and partitions. The works shall include:
* Civil works modifications
* Interior finishes
2. Deliverables
* Detailed architectural drawings
* Room layouts and 3D designs
* Implementation schedule
RFP (request for Proposal)
Space Standards and Components:
Each room will consist of demolition of wall partitions, disposal and replacing wall tiles, full WC renovation from removal and replace of ceiling, walls, floor tiles to be replaced including waterproofing, and provide WC accessories as per the bill of quantity provided. floorings to be carpet and supplying profile.
The BOQ and AutoCad proposed layout file attached with this proposal shall be followed exactly. All material specifications and brands are subject to approval of UHS engineering team.
Safety and Security:
The facility, fittings and equipment must be designed and constructed in such a way that all users of the facility are not exposed to avoidable risks of injury.
Finishes:
Finishes including building fabric, floor, wall and ceiling finishes, should be relaxing and noninstitutional as far as possible. The following additional factors should be considered in the selection of finishes:
1. acoustic properties
2. durability
3. ease of cleaning
4. infection control
5. fire safety
# Description of Material / Device Brand 1 Demolition Site preparation (including all required protections) Demolish and disposal of existing block wall partitions as per Proposed layout Remove and disposal of existing wall tiles as per proposed layout Remove and disposal of existing Sanitary wear and all accessories Remove and disposal of existing wall tiles for toilets Remove and disposal of existing floor tiles for toilets Remove and disposal of existing gypsum tiles 60x60 for toilets ceiling Remove and disposal of existing skirting Remove and disposal of existing aluminium cabinets Remove and disposal of existing aluminium doors Remove and disposal of existing exhaust (cooker hood) 2 Block work partitions as per new layout (all toilets): Supply and fix solid block 150 mm for the first line Supply and fix hollow block 150 mm for remaining lines Supply and install GI mesh at every three block rows Supply and cast reinforced lintel beam for the door or heavy duty Gi lintel Maintain curing for a minimum of 2-3 days 3 Plaster for walls include Supply and apply plaster with all required chemicals for new constructed
block partitions 4 Toilets work Flooring surface preparation for waterproof application Supply and apply two coats of cementitious waterproofing Waterproofing test Supply and install new RAK porcelain tiles 30x60 with waterproofing glue for walls Supply and install new RAK porcelain tiles 30x30 for floor Supply and install marble wash basin mixer Supply and install Shattaf KLUDI RAK Supply and install marble wash basin mixer Supply and install Shattaf KLUDI RAK Supply and fix Wall Mounted Bathroom Hardware Set Supply and fix W.C RAK Supply and fix gypsum celling 60x60 Supply and fix lighting 60x60 Supply and fix flow traps heavy duty supply and fix two marble counters 5 Gypsum partition works: Supply and fix 7 cm steel studs for the wall frame Supply and fix 75 mm covered Rockwall Supply and fix 12 mm waterproof gypsum boards double side Supply and apply stucco along the joint tape prepare the partition for the final painting 6 Chasing and cutting Chasing and cutting works for all electrical boxes 7 Flooring works include: Supply and apply 2 mm under lay layer Supply and apply 5 mm Carpet tiles Supply and apply profile on the required doorstep 8 Skirting works: supply and fix PVC skirting matching the carpet color. 9 Painting works include: Surface preparation for old walls Repair all existing cracks and close all holes using Jutton Stucco Surface preparation for new partitions by applying stucco and joint tapes Supply and apply two coats of anti-bacterial Jutton paint for the walls and ceiling 10 Wooden Door works for toilets: Supply and fix Five new doors for new toilets including all required accessories Painting the other doors to match new doors color 11 Aluminum windows work: Supply and fix two curtain wall to match the existing window with
dim of: 1300x2000 mm Maintenance work for cabinets door shutter replacement 12 Glass partition works in call center offices: Supply and fix 10 mm tempered glass partition using
stainless steel U channel with sandblast stickers
To participate in the tender and receive the AutoCad drawings please send an official email to Eng. Moza Alketbi - Moza.Alketbi@uhs.ae
Prepared & Arranged by:
Eng. Moza Alketbi
Facility Engineer
Verified & Approved by:
Eng. Noura Alawadhi
Director of Facility and Support Services